## Sheet1
Remaining Issues: Word Roots Flashcards
Level	Platform	Issue	Screenshot	Developer Response	Fixed?
1	iOS	Games 7 and 8 (really throughout the app): answer choices now seem not sensitive enough when selected; the black outline flickers when selected, and the answers don’t always appear in a selected state when selected. (The selected parts move to the correct place, but the selected parts don’t always remain outlined in black.)			Yes
1	iOS	Games 8 and 11: One page in each game opened with an answer already in a selected state. (This wasn’t an issue in Game 7 this time.)
1	iOS	I’m still not able to increase the volume much. It’s audible, but it should be able to be louder. ***The volume is not only too low throughout the app, there is also quite a lot of variation in volume levels. The new audio doesn’t match the volume level of the older stuff. ***I noticed this isn't an issue in Level 2, so there isn't a problem with the iPad.		The must be corrected on Scott's end	Yes
1	iOS	All platforms, re: the definition for “luminary”: We’ve added quotation marks around the word “star.” As long as you’re making other fixes, you may as well make this update too. Should be: “…a famous person (“star”).”		Fixed	Yes
All	iOS	All platforms: Put a space between the score and the correct/possible numbers. (This was fixed previously, so I think this is just an old version.) ***When a score of 100% is earned, and it's a game with 100+ words, there needs to be a space between those different numbers.		Fixed	Yes
1	iOS	Game 3: “go, yield” is shown twice as an answer choice.			Yes
1	iOS	***This edit may have been completed, but because the answer choices that show up are randomized, it’s difficult for me to check. Can you just confirm that this edit was done? All platforms, Game 10: One of the incorrect answer choices for “credulous” needs to be changed. We’re replacing “ence” with “cide.” Terry has updated the spreadsheet. (Can’t have “cred” and “ence” be options because “credence” is a word, but it’s not the correct answer.) ***Please leave a comment to confirm.		Confirmed fixed. The only incorrect parts that can be selected for “credulous” are: "ex","termin","clude","cide"
1	iOS	Game 11: move “word” so the sentence is on one line.			Yes
1	iOS	Game 11: For “innovate” we’re replacing “re” with another prefix. Terry will likely have updated the spreadsheet by the time you get these.			Yes
1	iOS	I played the games out of order. When I had completed all of them (ending with Game 9), the “Congratulations” box flashed on the screen for a split second but didn’t stay, and the “Next Game” button didn’t work.			Yes

All levels	iOS	4			Yes
All levels	iOS	Game Completed page: The text "Replay Incorrect Score" is overlapping the score.			Yes
All levels	iOS	The "Replay Incorrect Score" is showing up twice. This is from Game 10; this didn't occur in Game 2 when I used the "Replay Incorrect" option.			Yes
All levels	iOS	Games 1-3: The audio is occasionally glitching when an answer is selected. Games 4-6: Audio is stopping, then overlapping when an answer is selected. (Same issue as noted in previously Level 2). ***Audio was great for games 1-5, then started acting weird in Game 6: The audio for "ile" didn't play when an answer was selected, nor did the "as in" part of the answer. Other audio issue: Occasionally when an answer is selected, the audio for the word part and "as in" will play so close together it sounds odd, and then there will be a long pause before the audio for the example word plays.		I'm having trouble reproducing this. The issue with the delay between wordpart, “as in”, and example word should be resolved or at least less noticeable now. Here are some questions I have that might help resolve this issue: When you play through the activities, do you listen to all of the audio completely or do you skip some/all while it's playing (or in-between sounds)?	No
All levels	iOS	Throughout: The "next" arrows are sometimes shown already in a hover state. I haven't made a note of which pages this is on--hopefully you can just make a global change without going through and checking each page. ***In Level 1 this seemed to be completely resolved until Game 6, when at least one arrow showed up already in a hover state. I didn't notice a problem in games 7-12. In Level 2 it occurred a few times throughout the games.		The hover state should be completely removed on mobile versions. The button should fire its event on touch start (rather than on touch end as it was before)	No
All levels	All Platforms	Add updated Other Products page. ***Ask Terry where newest version is.		Added	Done in iOS L1; iOS L2 (still checking others)
All levels	All Platforms	Re: the app icon, is there a way to make the app border colors of L2 and L3 more distinguishable? It's nearly impossible to tell them apart on the screen.		I agree. I think all of the icons should be easier to distinguish from one another. The simplest solution I can think of would be to add a number to each icon. The only problem is the Beginning level (would be labeled “B” I guess, but that might still be somewhat confusing). Also some way to distinguish the demo icons from the full version icons (probably just the work “demo”)
All levels	iOS	If I touch the screen lightly to select an answer, the audio for the answer begins to play but then fades out. The answer eventually (but not always immediately) shows as highlighted in black. Is there a way to adjust the sensitivity? ***This occurred two or three times s in Game 1 of Level 1 and in several games of Level 2.		I'm unable to reproduce this, and I'm not sure what would cause it (I have no code that causes audio to fade out). As far as I know, we cannot adjust the screen sensitivity.
1	iOS	Game 11: "renovate," replace "ation" with "ition."		Confirmed
1	All Platforms	Game 11: "rejuvenate," replace "nov" with "lumin."		Confirmed

2	iOS	The audio is glitching; there's a break when some of the definitions play. Audio is also glitching and breaking in the games with "as in." Seems to be especially bad in Game 5. Same issue we had in Level 1.		Seems to be fixed	yes
2	All Platforms	Definition for suffix "ing": audio needs to be corrected. Definition is "relating to" but audio says "related to."		I'll need a new file from Scott	No
2	All Platforms	re: the app icon, is there a way to make the app border colors of L2 and L3 more distinguishable? It's nearly impossible to tell them apart on the screen.			Waiting on Scott/Julianna
2	iOS	Game 10: Can’t have both "itory" and "ancy" as answer choices. The correct answer is "dormancy," but "dormitory" is also a word (and there is no definition given in this game to eliminate options).		Fixed. Replaced itory with ory	yes
2	iOS	The "Congratulations" box came up when I had completed all games, but it only showed for about two seconds before disappearing.		Fixed	yes
2	iOS	Occasionally when an answer is selected and the page changes to the next word part, a different word part will appear for a split second in the yellow box at the top before the actual next word part appears. For example, I select an answer, then the screen flashes briefly on "nomin" before "duct" appears.			Yes
2	iOS	Game Completed page: The text "Replay Incorrect Score" is overlapping the score.			Yes
All levels	iOS	Throughout: The "next" arrows are sometimes shown already in a hover state. I haven't made a note of which pages this is on--hopefully you can just make a global change without going through and checking each page.

Beg.	All Platforms	Definition for suffix "ly" has only part of the audio. Audio says, "in the manner of," but it should say, "in the manner of; having the quality of."		I'll need a new file from Scott
Beg.	All Platforms	Root "vers": We need two pronunciations. We only give /vurzh/ but we also need /vurse/ as in "reversible."		I'll need a new file from Scott
Beg.	All Platforms	Word "flexor": We should have new audio for this word. Current audio sounds like "fluxor."		I'll need a new file from Scott
Beg.	All Platforms	Game 9: Can't have "un" as an answer choice. Replace with "dis."		Replaced “dis” with “im”
Beg.	All Platforms	Game 10: Can't have "dign" as an answer choice. Replace with "sens."		“contact” is not in beginning level data
Beg.	All Platforms	Crap crap crap; I obviously didn't check this page carefully in the Beginning level, because the info here doesn’t match the number of games offered. ***Make same change to Demo.		Fixed
Beg. Demo	All Platforms	The Beginning level has 10 games, but the Beginning Demo is showing a Home page with 12 games (screenshot on left); need to add the correct Home page.		Fixed
Beg. Demo	All Platforms	I wasn't able to move beyond this screen; the "Next Game" button was stuck on the hover state, and none of the other buttons worked either. After this I wasn't able to get any of the games to work, even after closing it out and reopening.		Fixed

3	All Platforms	Game 7, "onymous": Can't have "ant" as an answer choice. Replace "ant" with "anti."		Confirmed
3	All Platforms	Game 7, "logic," Can't have "ics" as an answer choice. Replace "ics" with "ism."		Confirmed
3	All Platforms	Game 7, "monochrome," replace "bi" with "de."		Confirmed
3	All Platforms	Game 8: There are only three answer choices for "agronomy." Need an incorrect choice added: add "anti." And the correct answer shows as incorrect when the word parts are selected.		Replaced “y” with “ium”
3	All Platforms	Game 11: There are only three answer choices for "anarchy." Need an incorrect choice added. Add "counter." (Correct answer is showing as incorrect.)		Replaced “y” with “ial”
3	All Platforms	Game 10: "perimeter," replace "tele" with "scope."		Replaced “scope” with “scop”
3	All Platforms	Game 10: "monochrome," replace "bi" with "astro."		Neither “bi” or “astro” are in my word list
3	All Platforms	Game 10: "cardiology," replace "nomo" with "nome."		Confirmed
3	All Platforms	Game 10: "diagram," replace "micro" with "meso."		Confirmed
3	All Platforms	Game 11: "pathogenic," replace "eu" with "exo."		Confirmed
3	All Platforms	Game 11: "theonomy," replace "anti" with "ant."		Confirmed
3	All Platforms	Game 11: "polygenic," replace "hypo" with "peri."		Confirmed
3	All Platforms	Game 11: "neography," replace "crac" with "clast."		Confirmed
3	All Platforms	Game 11: "psychogenic," replace "bio" with "grapho."		Confirmed