## Sheet1
Remaining Issues: Word Roots Flashcards
Level	Platform	Issue	Screenshot	Developer Response	Fixed?
1	iOS	Games 7 and 8 (really throughout the app): answer choices now seem not sensitive enough when selected; the black outline flickers when selected, and the answers don’t always appear in a selected state when selected. (The selected parts move to the correct place, but the selected parts don’t always remain outlined in black.)			Yes
1	iOS	Games 8 and 11: One page in each game opened with an answer already in a selected state. (This wasn’t an issue in Game 7 this time.)
1	iOS	I’m still not able to increase the volume much. It’s audible, but it should be able to be louder. ***The volume is not only too low throughout the app, there is also quite a lot of variation in volume levels. The new audio doesn’t match the volume level of the older stuff. ***I noticed this isn't an issue in Level 2, so there isn't a problem with the iPad.		The must be corrected on Scott's end	No
1	iOS	All platforms, re: the definition for “luminary”: We’ve added quotation marks around the word “star.” As long as you’re making other fixes, you may as well make this update too. Should be: “…a famous person (“star”).”		Fixed	Yes
All	iOS	All platforms: Put a space between the score and the correct/possible numbers. (This was fixed previously, so I think this is just an old version.) ***When a score of 100% is earned, and it's a game with 100+ words, there needs to be a space between those different numbers.		Fixed	No
1	iOS	Game 3: “go, yield” is shown twice as an answer choice.			Yes
1	iOS	***This edit may have been completed, but because the answer choices that show up are randomized, it’s difficult for me to check. Can you just confirm that this edit was done? All platforms, Game 10: One of the incorrect answer choices for “credulous” needs to be changed. We’re replacing “ence” with “cide.” Terry has updated the spreadsheet. (Can’t have “cred” and “ence” be options because “credence” is a word, but it’s not the correct answer.) ***Please leave a comment to confirm.		Confirmed fixed. The only incorrect parts that can be selected for “credulous” are: "ex","termin","clude","cide"
1	iOS	Game 11: move “word” so the sentence is on one line.			Yes
1	iOS	Game 11: For “innovate” we’re replacing “re” with another prefix. Terry will likely have updated the spreadsheet by the time you get these.			Yes
1	iOS	I played the games out of order. When I had completed all of them (ending with Game 9), the “Congratulations” box flashed on the screen for a split second but didn’t stay, and the “Next Game” button didn’t work.			Yes
Level 2
2	iOS	The audio is glitching; there's a break when some of the definitions play. Audio is also glitching and breaking in the games with "as in." Seems to be especially bad in Game 5. Same issue we had in Level 1.		Seems to be fixed	yes
2	iOS	Audio: 1) Need two pronunciations for root "capit," which have been recorded, just need to be added. 2) Need different audio for root "veloci." 3) Need new audio for root "gnos." 4) Need audio for root "esticate" and its definition: "to make, to act; one who, that which." 5) Need new audio for root "esis." 6) Need an additional pronunciation for root "peri." 7) Need a different pronuncitation of root "nox." 8) Need a different pronunciation of root "auxano." 9) need an additional pronunciation for root "soci."
2	iOS	Game 10: Can’t have both "itory" and "ancy" as answer choices. The correct answer is "dormancy," but "dormitory" is also a word (and there is no definition given in this game to eliminate options).		Fixed. Replaced itory with ory	yes
2	iOS	The "Congratulations b"ox came up when I had completed all games, but it only showed for about two seconds before disappearing.		Fixed	yes